## Sheet1
Pending and In-Process Renewable Energy Project Applications - BLM Nevada 10/29/2021
| Total Pending (auth. not included) | In Cue/Pending | In Process Pre-Variance | In Process Pre-NEPA | In Processs NEPA (public notice out) | Total In Process Pre-Variance/Pre-NEPA/NEPA | Authorized LNTP/NTP / Construction
BMDO | 14 | 4 | 7 | 3 |  | 10
SNDO | 24 | 18 | 6 |  |  | 6 | 3
CCDO | 10 | 1 | 4 | 3 | 2 | 9
Ely DO | 4 | 4 |  |  |  | 0
Winn. DO | 7 | 0 |  | 6 | 1 | 7 | 4
Elko DO | 1 | 0 |  | 1 |  | 1
Major Transm. | 2 | 0 |  | 2 |  | 2 | 1
TOTAL BLM NEVADA | 62 | 27 | 17 | 15 | 3 | 35 | 8
District | On HQ Renew. Energy Dashboard | Count | Type |  | Name of project | Applicant Name | Serial Number | Date of App | Status | Status Notes | Planned date to finish variance or finish NEPA | MWs | Energy storage
BATTLE MOUNTAIN DISTRICT |  | 1 | Solar | Esmerald Variance Group | Esmeralda Solar Energy Project | Leward (was First Solar) | N-100222 | 2021-01-21 | Pre variance | Sept. 2021: Variance public meetings complete; Oct. 2021: Variance report and concurrence package in preparation (expected early Nov. 2021) | TBD | 650 | Y
|  | 2 | Solar |  | Smoky Valley | ConnetGen | N-100223 | 2021-01-22 | Pre variance |  | TBD | 1000 | Y
|  | 3 | Solar |  | Gold Dust | Ariva | N-100357 | 2021-04-06 | Pre variance |  | TBD | 1500 | Y
|  | 4 | Solar |  | Nivloc | Invenergy | N-100358 | 2021-04-05 | Pre variance |  | TBD | 500 | Y
|  | 5 | Solar |  | Esmeralda Solar Energy Center | NextEra | N-100361 | 2021-04-09 | Pre variance |  | TBD | 500 | Y
|  | 6 | Solar |  | Rhyolite Ridge #1 | 8-Minute Energy | N-100397 | 2021-04-28 | Pre variance |  | TBD | 600 | Y
|  | 7 | Solar |  | Rhyolite Ridge #2 | 8-Minute Energy | N-100398 | 2021-04-28 | Pre variance |  | TBD | 600 | Y
|  | 8 | Solar |  | Sawtooth | NextEra | N-100389 | 2021-04-28 | Pre variance |  | TBD
|  | 11 | Solar |  | Beatty | NextEra | N-100475 | 2021-06-07 | Pre variance |  | TBD
| X | 12 | Geo |  | Fish Lake Utilization Plan | Open Mountain Energy / Fish Lake Geot. | N-056345-X | 2021-05-11 | Pre-NEPA | Baseline studies underway | TBD Est.: Prelim. EA - 7/1/2022 DR/FONSI: Q1 FY 2023 | 20
|  | 13 | Geo |  | Lone Mountain Geothermal | Ormat | N-097643 et al | 2021-02-04 | Pre-NEPA | Baseline studies underway | TBD
|  | 14 | Geo |  | Pearl Hot Springs | Ormat | N-094095 et al | 2021-05-19 | Pre-NEPA | Baseline studies underway | TBD
SOUTHERN NEVADA DISTRICT | X | 1 | Solar |  | Copper Rays Solar Project | Leward (was First Solar) | TBD | 2010-09-09 | Pre variance | Oct. 2021: Segregation FRN published; Variance public mtg. est. 1/2022 | TBD Est. NOI - Spring 2022 ROD - Q3 FY 2022 | 700
| X | 2 | Solar |  | Rough Hat Nye Solar Project | Candella | TBD | 2019-11-14 | Pre variance | Oct. 2021: Segregation FRN published; Variance publc mtg. est. 11/2021 | TBD Est. ROD - Q 3 FY 2022 | 500
| X | 3 | Solar |  | Rough Hat Clark Solar Project | Candella | TBD | 2019-11-14 | Pre variance | Oct. 2021: Segregation FRN published; Variance publc mtg. est. 11/2021 | TBD Est. ROD - Q3 FY2022 | 400
|  | 4 | Solar |  | Nevada Edge | EDF | TBD | 2013-12-05 | Pre variance |  | TBD
|  | 5 | Solar |  | South Solar Ridge | Leeward | N-086782 | 2009-02-23 | Pre variance |  | TBD
|  | 6 | Solar |  | Meadow Valley | Mesa Solar Energy | N-092032 | 2013-05-01 | Pre variance |  | TBD
|  | 7 | Solar |  | Laughlin | Leeward | N-092261 | 2013-07-19 | Pre variance |  | TBD
|  | 8 | Solar |  | Snow Mountain | Leeward | N-093615 | 2014-11-25 | Pre variance |  | TBD
|  | 9 | Solar |  | Red Valley | Leeward | N-097775 | 2018-04-04 | Pre variance |  | TBD
|  | 10 | Solar |  | Red Flats | Leeward | N-097778 | 2013-11-26 | Pre variance |  | TBD
|  | 11 | Solar |  | Playa Del Sol Solar Project (near solar project on BIA; Arrow Canyon Solar) | EDF Renewable Energy, llc | N-099950 | 2020-09-04 | Pre variance |  | TBD
|  | 12 | Solar |  | Townsite Solar Project Expansion Eldorado Valley | Skylar Energy Resources, LLC | N-099875 | 2020-06-08 | Pre variance |  | TBD
| X* | 13 | Solar |  | Bonanza Solar Project | Bonanza Solar, LLC | N-100224 | 2020-12-04 | Pre variance | FAST-41 Prioritization complete; Variance process to commence 9/2022 | FAST-41 CPP Timeline Variance Process 9/2022 - 2/2023 NOI - 3/2024 NOA DEIS - 10/2024 NOA FEIS/RMPA - 6/2025 ROD - 10/2025 ROW Grant - 1/2026 | 600 | Y
|  | 14 | Solar |  | Solar 373 | Arevia Power | N-100386 | 2021-04-05 | Pre variance | SNDO working with project proponent on completing application and will accept app. fee for non-competitive process (previously planned to go competitive) | TBD
|  | 15 | Solar |  | Sagittarius Solar | Noble Solar, LLC c/o Arevia Power | N-100225 | 2020-11-09 | Pre variance |  | TBD
|  | 16 | Solar |  | Amargosa East Solar Project | US Solar Assets LLC | N-100448 | 2021-04-02 | Pre variance |  | TBD
|  | 17 | Solar |  | Amargosa West Solar Project | US Solar Assets LLC | N-100449 | 2021-04-02 | Pre variance |  | TBD
|  | 18 | Solar |  | Angora Solar Project | 328CH 8me LLC | N-100537 | 2021-06-17 | Pre variance |  | TBD
|  | 19 | Solar |  | Virgo Solar | Arevia Power | N-100538 | 2021-06-23 | Pre variance | SNDO working with project proponent on completing application and will accept app. fee for non-competitive process (previously planned to go competitive) | TBD
|  | 20 | Solar |  | Jackass Flats Solar Facility | EDF Renewables Development | TBD | 2021-06-21 | Pre variance |  | TBD
|  | 21 | Solar |  | SB Solar Plant | EDF Renewable Development | TBD | 2021-06-21 | Pre variance |  | TBD
|  | 22 | Solar |  | Northwest Solar Facility | EDF Renewable Development | TBD | 2021-06-21 | Pre variance |  | TBD
| X* | 23 | Wind |  | Kulning Wind Energy Project | Crescent Peak Renewables, LLC | N-100347 | 2021-03-03 | Pre variance | FAST-41 CPP Due - 11/29/2021 | TBD
| X | 24 | Solar |  | Dry Lake East Designated Leasing Area Competitive Lease Sale |  |  |  | Pre-Notice of Competitive Sale | Sept. 2021: Draft Notice of Competitve Offer (NOCO) FR Notice to SNDO for review. 10/2021 | TBD Est. - NOCO 1/2022
|  | 25 | Solar |  | Yellow Pine | Nextera | N-90788 |  | NTP | 10/29/2021: LNTPs Issued; Geotech occuring Final NTP pending
|  | 26 | Solar |  | Gemini | Ariva | N-84631 |  | NTP | 10/29/21: LNTP for fencing issued 3/2021; Desert Tortoise translocation underway; SNDO reviewing POD and reclamation cost estimate; Final NTP pending
|  | 27 | Solar |  | Dry Lake | NV Energy | N-93337 |  | NTP
CARSON CITY DISTRICT |  | 1 | Solar |  | Libra Solar | Ariva | N-099846 | 2020-09-16 | Pre variance | Variance Public Mtg Complete Variance Report/Package Being Prepared | Q4 2021
|  | 2 | Solar |  | Dodge Flat II | NextEra | N-100104 | 2020-11-15 | Pre variance | Variance Public Mtg Complete 10/2021 - Variance Package Routed for Concurrence | Q1 2022
|  | 3 | Solar |  | Mason Valley | NextEra | N-100105 | 2020-11-19 | Pre variance | Variance Public Mtg Complete Expecting variance package from contractor late Oct or early Nov 2021 | Q1 2022
|  | 4 | Solar |  | Pine Nut | NextEra | N-100106 | 2020-11-19 | Pre variance | Variance Public Mtg Complete Expecting variance package from contractor late Oct or early Nov 2021 | Q1 2022
|  | 5 | Wind |  | Comstock Wind | Crescent Peak Renewables, LLC | N-098533 | 2017-09-17 | Pre NEPA |  | TBD
| X | 6 | Geo |  | Dixie Meadows Geothermal | ORMAT | N-089456X | 2015-05-01 | NEPA | On-Hold Pending FWS listing determination DV Toad |  | 60
|  | 7 | Geo |  | Diamond Flat Geothermal (Exploration) | ORMAT | N-073679/073930 | 2021-02-09 | Pre-NEPA | Baseline studies underway | TBD
|  | 8 | Geo |  | Don Campbell | ORMAT | N-084239X | 2020-04-06 | Pre-NEPA |  | TBD
|  | 9 | Geo |  | Comstock Geothermal Exploration | ORMAT | N-094093 et al | 2019-01-01 | NEPA | Draft EA with NEPA contractor | TBD
| X | 10 | Solar |  | Luning II Solar | Liberty Utilities |  |  | NEPA | EA Public Comment - 9/23 - 10/25/21 | Est. DR FONSI - 12/15/2021 | 50 | Y
ELY DISTRICT |  | 1 |  |  | All projects are a combination of wind and solar under Site type II testing. Sage grouse issues needs resolution |  | N-100123 | TBD | TBD |  | TBD
|  | 2 |  |  |  |  | N-100123 | TBD | TBD |  | TBD
|  | 3 |  |  |  |  | N-099861 | TBD | TBD |  | TBD
|  | 4 |  |  |  |  | N-089476 | TBD | TBD |  | TBD
WINNEMUCCA DISTRICT |  |  | Wind | No current projects. Greenlink North is expected to generate interest.
Solar
| X | 1 | GEO |  | Noth Valley Juniper - Utilization Plan | Ormat | NVN-093716X | 2019-10-31 | Pre-NEPA | Baselines underway | TBD | 60
| X | 2 | GEO |  | Star Peak - Humboldt House Utilization Plan | Open Mountain | NVN-58323X | 2021-05-18 | Pre-NEPA | Collecting Baselines; Preliminary Tribal Consultation; Pending Modification to Utilization Plan | TBD | 48
|  | 3 | GEO |  | Gerlach | Ormat | NVN-88151X | 2021-12-30 | Pre-NEPA | Baselines underway | TBD
|  | 4 | GEO |  | Pinto Hot Springs (Exploration) | Ormat | NVN-98637/98638 | 2021-06-28 | Pre-NEPA | Baselines underway | TBD
|  | 5 | GEO |  | McGee | Ormat | NVN-98639/98646 | 2021-06-02 | Pre-NEPA | Baselines underway | TBD
|  | 6 | GEO/Transmission |  | New York Canyon (T-Line ROW only) | Ormat | NVN-88828X | Pending | Pre-NEPA | 10/2021: Ormat recently decided on location for line; NEPA initiation to follow | TBD
|  | 7 | Transmission (Transmission and Road on BLM; Solar on Private) |  | Grass Valley | Leeward | NVN-99575 NVN-99827 |  | NEPA | 10/29/2021: Solar on private land; transmission and road on BLM. DNA for BLM trans./road authorization nearly complete and finalization is expected early Nov. 2021 | Est. Approval of BLM portion - Early Nov. 2021 | 340
| X | 8 | GEO |  | San Emidio | Ormat |  |  | Authorized NTP/Construction Pending | DR Signed - 5/21/2021 Construction permit was submitted 8/25/2021 by Ormat and is currently being reviewed by the WDO. 10/28/21: site license and commercial use permit (CUP) will be submitted. Once the Black Rock FO accepts the water monitoring plan, conditions of approval (COAs) will be drafted for the geothermal drilling permits (GDPs).
| X | 9 | GEO |  | Baltazar | Ormat |  |  | Authorized NTP/Construction Pending | DR signed - 5/21/2021 10/28/21 - Construction permit, site license and CUP have not been submitted yet by Ormat.
|  | 10 | Solar |  | Hot Pot |  |  |  | Authorized NTP/Construction Pending
|  | 11 | Solar |  | Iron Point |  |  |  | Authorized NTP/Construction Pending
ELKO DISTRICT |  | 1 | GEO |  | Crescent Valley (Exploration) | Ormat | N-074266 et al | 2021-03-03 | Pre-NEPA | Baselines underway; 10/2021 - Expect draft EA from contractor soon and public scoping late Oct. 2021 or early Nov. 2021 | TBD
MAJOR TRANSMISSION PROJECTS | X | 1 | Transmission |  | Greenlink West | [5 empty] | Est. NOI - 4/2022 NOA DEIS - 12/2022 NOA FEIS/RMPA - 4/2023 ROD -7/2023
| X | 2 | Transmission |  | Greenlink North | [5 empty] | Essentially 1 year behind Greenlink West
| X | 3 | Transmission |  | Southwest Intertie Project (SWIP) North
X* To be added to Renewable Energy Dashboard at next available opportunity (11/1/2021)